## main_plan
Day | Timestamp (Eastern) | Tasks: | Assigned To: | Date Completed: | Estimated Time:
2022-09-19 |  | Review proposals & determine direction of project | Group | 2022-09-19 | 3 hours | Important Info
|  | EDA on whole dataset | Stephanie | 2022-09-19 | 2 hours | Storage Container | group-2-capstone
|  | EDA on $150k+ dataset | Emily | 2022-09-19 | 2 hours | SQL DB | group-2-capstone
|  | EDA on unemployment data | Nolan | 2022-09-19 | 2 hours | SQL DB username | group_2
|  | EDA on Census data | Adam | 2022-09-19 | 2 hours | SQL DB password | Sp0ngeB0b
[6 empty] | confluentTopicName | group-2-PPP
2022-09-20 |  | Review EDA | Group | 2022-09-20 | 1 hour | confluentClusterName | group-2-PPP
|  | Define questions and topic | Group | 2022-09-20 | 30 mins | AccessToken Data Fac | dapie88ede0246e3cec6dc14370a1c63ee3f-2
|  | Refine PMP | Emily | 2022-09-20 | 2 hours
|  | Combine all PPP datasets & merge NAICS code/industry name | Stephanie | 2022-09-20 | 2 hours
|  | Explore BLS API | Emily | 2022-09-20 | 1 hour
|  | Select Census data | Adam | 2022-09-20 | 2 hours
|  | Draft elevator pitch | Nolan | 2022-09-20 | 1 hour
|  | Draft executive summary | Nolan | 2022-09-20 | 2 hours
|  | Initial clean of PPP data | Stephanie | 2022-09-20 | 2 hours
|  | Edit pitch/summary | Nolan | 2022-09-20 | 2 hours
Evening
|  | First draft of ERD | Nolan | 2022-09-20 | 3 hours
|  | Proofread ERD | Adam | 2022-09-20 | 30 mins
|  | Normalize ERD | Adam | 2022-09-20 | 1 hour
|  | Review content in LMS | Group | 2022-09-20 | 1 hour
2022-09-21 | 10:15 - 10:30 | Daily Debrief | Group | 2022-09-21 | 15 mins
| 10:30 - 10:45 | Decide on final PPP rows | Group | 2022-09-21 | 15 mins
| 10:45 - 1:45 | Edit/Finalize ERD | Adam | 2022-09-21 | 3 hours
| 11:00 - 1:00 | Further cleaning PPP data | Stephanie | 2022-09-21 | 2 hours
| 2:00 - 3:30 | Finalize PPP data | Stephanie | 2022-09-21 | 2 hours
|  | Clean unemployment data | Emily | 2022-09-20
|  | Clean Census data | Adam | 2022-09-20
| 11:30 - 12:30 | Write intro for ETL report draft | Nolan | 2022-09-21 | 1 hour
| 11:30 - 12:30 | Merge all data cleaning notes for ETL report draft | Adam | 2022-09-21 | 1 hour
| 12:30 - 4:30 | Move data cleaned into storage container | Adam | 2022-09-21 | 3 hours
| 2:00 - 4:00 | DDL | Nolan | 2022-09-21 | 2 hours
| 3:30 - 5:00 | Write data cleaning ETL report for PPP, Census, Unemp stpes | Stephanie | 2022-09-21 | 2 hours
| 2:00 - 3:00 | Create SQL Database | Emily | 2022-09-21 | 1 hour
Evening
|  | Finalize DDL | Nolan | 2022-09-21 | 1 hour
|  | First attempt at Kafka producer | Stephanie | 2022-09-21 | 2 hours
|  | Internalize Kafka procedures, give it a go? | Emily, Adam, Stephanie | 2022-09-21 | 2 hours
2022-09-22 | 10:15 - 10:30 | Daily Debrief | Group | 2022-09-22 | 15 mins
| 10:30 - 10:45 | Review any sticking points from ETL/ERD | Group | 2022-09-22 | 15 mins
| 10:30 - 11:00 | Finalize first two sections of ETL report | Stephanie | 2022-09-22 | 30 mins
| 10:30 - 11:00 | Finalize DDL | Nolan | 2022-09-22 | 30 mins
| 11:00 - 12:00 | PDF of data sources | Nolan | 2022-09-22 | 1 hour
| 11:00 - 1:00 | Create Kafka Unemployment consumer | Stephanie | 2022-09-22 | 2 hours
| 11:00 - 12:00 | Research populators | Emily | 2022-09-22 | 1 hour
| 12:00 - 1:00 | Finalize PMP | Emily | 2022-09-22 | 1 hour
| 11:00 - 1:00 | Create diagram of data flow | Nolan | 2022-09-22 | 1 hour
| 12:00 - 1:00 | Begin creating populators | Adam | 2022-09-22 | 1 hour
| 2:00 - 5:00 | Continue with populators | Adam | 2022-09-22 | 3 hours
| 2:00 - 3:00 | Compile deliverables, Git push | Emily | 2022-09-22 | 2 hours
| 2:00 - 5:00 | Kafka producer/consumer | Stephanie | 2022-09-22 | 3 hours
| 2:00 - 4:00 | Diagram/document cloud servers | Emily | 2022-09-22 | 2 hours
| 4:00 - 5:00 | Check on first week deliverables | Group | 2022-09-22 | 1 hour
Evening
|  | Settle foreign keys and push all tables to SQL | Stephanie | 2022-09-22 | 2 hours
|  | Settle foreign keys and push all tables to SQL | Adam | 2022-09-21 | 2 hours
2022-09-23 | 10:15 - 10:30 | Daily Debrief | Group | 2022-09-23 | 15 mins
| 10:15 - 10:30 | Review Project Sources | Adam | 2022-09-23 | 15 mins
| 10:30 - 10:45 | Review Executive Summary | Emily | 2022-09-23 | 15 mins
| 10:30 - 10:45 | Review Data Platform Diagram/Documentation | Nolan | 2022-09-23 | 15 mins
| 10:30 - 10:45 | Review Project Plan | Stephanie | 2022-09-23 | 15 mins
| 11:00 - 1:00 | Dash/Plotly Review | Group | 2022-09-23 | 2 hours
| 2:00 - 4:30 | Create Data Factory | Adam | 2022-09-23 | 2 hours
| 2:00 - 4:30 | Research/begin implementing ML model | Emily | 2022-09-23 | 2 hours
| 2:00 - 4:30 | Update repeatable ETL with databrick/producer/consumer loading | Stephanie | 2022-09-23 | 2 hours
| 2:00 - 4:30 | Research/begin implementing ML model | Nolan | 2022-09-23 | 2 hours
| 4:30 - 5:00 | Prep for weekend | Group | 2022-09-23 | 1 hour
Weekend |  | Convert all cleaning to pyspark on databrick | Stephanie |  | 6 hours
|  | Convert all cleaning to pyspark on databrick | Adam |  | 6 hours
|  | Upload data to SQL Database | Adam |  | 6 hours
|  | Run Random Forest ML model | Nolan |  | 3 hours
|  | Run K-Nearest Neighbor ML model | Emily |  | 3 hours
2022-09-26 | 10:15 - 10:30 | Daily Debrief | Group |  | 15 mins
| 10:30 - 10:45 | Discuss ML models | Group |  | 15 mins
| 10:45 - 11:00 | Discuss ETL | Group |  | 15 mins
| 11:00 - 12:00 | Napkin drawings | Group |  | 1 hour
| 12:00 - 12:30 | Gather and document feedback | Group |  | 30 mins
| 12:30 - 1:00 | Revise napkin drawings | Group |  | 30 mins
| 2:00 - 5:00 | Update ETL so far with cleaning/transforming/loading on databrick | Stephanie |  | 3 hours
| 2:00 - 5:00 | Fine tune ML model (KNN) | Emily |  | 3 hours
| 3:00 - 5:00 | Populators | Adam |  | 3 hours
| 3:00 - 5:00 | Fine tune ML model (RF) | Nolan |  | 3 hours
Evening
|  | Implement ML model with SQL data |  |  | 3 hours
|  | Create napkin drawings for dashboard | Group |  | 3 hours
2022-09-27 | 10:15 - 10:30 | Daily Debrief | Group |  | 15 mins
| 10:30 - 11:00 | Discuss dashboard/napkin drawings | Group |  | 30 mins
| 11:00 - 11:30 | Gather and document feedback | Group |  | 30 mins
| 11:30 - 1:00 | Begin visuals | Team 1 |  | 1.5 hours
| 11:30 1:00 | Begin dashboard | Team 2 |  | 1.5 hours
| 2:00 - 5:00 | Dashboard | Team 1 |  | 3 hours
| 2:00 - 5:00 | Visuals | Team 2 |  | 3 hours
Evening
|  | Continue work on Dashboard | Team 1 |  | 2 hours
|  | Continue work on visuals | Team 2 |  | 2 hours
2022-09-28 | 10:15 - 10:30 | Daily Debrief | Group |  | 15 mins
| 10:30 - 11:00 | Review progress on dashboard/ML | Group |  | 30 mins
| 11:00 - 1:00 | Dashboard | Stephanie |  | 2 hours
| 11:00 - 1:00 | Visuals | Nolan |  | 2 hours
| 11:00 - 1:00 | Finish tuning ML model | Emily |  | 2 hours
| 11:00 - 1:00 | Finalize visualization napkin drawing/feedback document | Adam |  | 2 hours
| 2:00 - 5:00 | Dashboard | Group |  | 3 hours
Evening
|  | Finalize Dashboard | Group |  | 2 hours
2022-09-29 | 10:15 - 10:30 | Daily Debrief | Group |  | 15 mins
| 10:30 - 1:00 | First draft of technical report introduction | Adam |  | 2 hours
| 10:30 - 1:00 | First draft of technical report research presentation | Emily |  | 2 hours
| 10:30 - 1:00 | First draft of technical report conclusion | Nolan |  | 2 hours
| 10:30 - 1:00 | First draft of Read Me | Stephanie |  | 2 hours
| 2:00 - 5:00 | First draft of technical report introduction | Adam |  | 3 hours
| 2:00 - 5:00 | First draft of technical report research presentation | Emily |  | 3 hours
| 2:00 - 5:00 | First draft of technical report conclusion | Nolan |  | 3 hours
| 2:00 - 5:00 | First draft of Read Me | Stephanie |  | 3 hours
2022-09-30 | 10:15 - 10:30 | Daily Debrief | Group |  | 15 mins
| 11:00 - 12:00 | Compile/begin editing technical report | Group |  | 1 hour
| 12:00 - 1:00 | Initial Questions Slides | Adam |  | 1 hour
| 12:00 - 1:00 | Research Questions Slides | Emily |  | 1 hour
| 12:00 - 1:00 | Machine Learning Slides | Stephanie |  | 1 hour
| 12:00 - 1:00 | Reccommendation Slides | Nolan |  | 1 hour
| 2:00 - 4:00 | First run of presentation/edit slides | Group |  | 2 hours
| 4:00 - 5:00 | Git push, check on deliverables | Group |  | 1 hour
Weekend |  | Slides
Read Me
Technical report
2022-10-03 | 10:30 -11:30 | Status report of all deliverables | Group |  | 1 hour
| 11:30 - 1:00 | Finalize technical report | Team 1 |  | 1.5 hours
| 11:30 - 1:00 | Finalize slides, Read Me | Team 2 |  | 1.5 hours
| 2:00 - 5:00 | Flex time - Git push - Compile deliverables - Clean Google Drive/polish deliverables | Group |  | 3 hours
2022-10-04 |  | Flex
2022-10-05 |  | Rehearsal | Group

## week_1
Deliverable | Description | Done? | Pushed to Git?
Git repository | Contains folder "ProjectSpecifications" | TRUE | TRUE
Executive Summary | Saved as "ExecutiveSummary.pdf" | TRUE | TRUE
Data Platform Diagram | Save Diagram and Documentation as one PDF named 'DataPlatform.pdf' | TRUE | TRUE
Data Platform Documentation
Project Plan | Saved as "ProjectPlan.xlsx" | TRUE | TRUE
Data Sources | Annotated list of all data sources - URL of data source - Description Saved as "DataSources.pdf" | TRUE | TRUE

## Rubric
Item | Meets Expectations 2 points | Not Yet 1 point | No Attempt 0 points
Deliverables
GitHub URL | GitHub repo URL is submitted properly. | Another source control tool is used. | No GitHub repo. No source control.
Exploratory Questions | 5-10 exploratory questions have been presented in a file named ExploratoryQuestions.pdf. | Less than 5 or more than 10 questions are presented. Exploratory questions are in a file not named properly. | No exploratory questions.
Project Management Plan | A complete project management plan has been submitted in a file named ProjectManagementPlan.pdf | An incomplete project management plan has been submitted and/or the file is not named properly. | No project management plan.
Napkin Drawings & Feedback for Visualizations | Napkin drawings and feedback for visualizations are included in a file named VisualizationsNapkinsAndFeedback.pdf | Napkin drawings for visualizations and/or feedback is missing. Napkin drawings and feedback for visualization are included but not named properly. | No napkin drawings and feedback for visualizations.
Napkin Drawings & Feedback for the Dashboard | Napkin drawings and feedback for the dashboard are included in a file named DashboardNapkinsAndFeedback.pdf | Napkin drawings for the dashboard and/or feedback are missing. Napkin drawings and feedback for the dashboard are included but not named properly. | No napkin drawings and feedback for the dashboard.
Repeatable ETL Report | Repeatable ETL Report is included in a file named RepeatableETLReport.pdf | ETL report is not repeatable. ETL report is not named properly. | No Repeatable ETL report.
Dashboard | A dashboard is created with Dash or a report in Power BI with Python. All code for the dashboard or report is included in a code folder in the repo. | A dashboard is created with a different technology. No code is stored in the code folder. Code may be stored in a folder not properly named. | No dashboard and no code for the dashboard.
Project Technical Report | The project technical report is in a file named ProjectTechnicalReport.pdf | The project technical report is not named properly. | No project technical report.
Presentation Slides | Presentation slides are included in a file named CapstonePresentationSlides.pdf | Presentation slides are not included - only a URL is included. Presentation slides are in a file not properly named. | No presentation slides.
GitHub Repo
README | GitHub repo contains a README that details the repo and makes it easy to navigate. | GitHub repo contains a README that has some information but leaves things out in terms of understanding the repo. | No README file in the repo.
Organization | GitHub repo is well organized and easy to navigate. | GitHub repo is somewhat organized - has folders and files are named reasonably. Organization is clumsy. | No organization in the GitHub repo.
Data
Census Data | One of the provided Census dataset links was used. | Census data was used but it wasn't one of the provided Census dataset links. | No Census data.
Tools
Python | Python code is well-organized, readable, and completely functional. | Python code is not organized or somewhat unreadable. Python code may be partially functional or broken. | No Python used.
pandas/pyspark | pandas/pyspark functions properly for ETL in Python. | pandas/pyspark is used but is not functional. | No pandas/pyspark used.
Project Plan
Task Division | All tasks look to be evenly split among team members. | Tasks are broken down but not granular enough to judge whether work is evenly split. Tasks are not evenly split among team members. | Tasks aren't broken down and assigned evenly to team members.
Exploratory Questions | Project plan accounts for Exploratory Questions. | No halfway point. | Project plan does not include Exploratory Questions.
Napkin Drawings & Feedback for Visualizations | Project plan accounts for napkin drawings of the visualizations and their feedback. | No halfway point. | Project plan does not include Napkin Drawings and Feedback for visualizations.
Napkin Drawings + Feedback for the Dashboard | Project plan accounts for napkin drawings of the dashboard and their feedback. | No halfway point. | Project plan does not include Napkin Drawings and Feedback for the dashboard.
Repeatable ETL Report | Project plan accounts for the repeatable ETL report. | No halfway point. | Project plan does not include creating the repeatable ETL report.
Dashboard | Project plan accounts for building a dashboard in Dash or report in Power BI with Python. | No halfway point. | Project plan does not include building a dashboard in Dash or Power BI with Python.
Project Technical Report | Project plan accounts for technical report summary. | No halfway point. | Project plan does not include the project technical report.
Presentation Slides | Project plan accounts for presentation slides. | No halfway point. | Project plan does not include presentation slides.
Presentation Dry Run | Project plan accounts for presentation dry run. | No halfway point. | Project plan does not include presentation dry run.
Napkin Drawings and Feedback for Visualizations
Visualization Napkin Drawing Quality | Visualization napkin drawings are minimalist, little to no styling, and enough to get the point across on what is being represented. | Visualization napkin drawings have styles that make them closer to the finished product. Napkin drawings don't clearly convey their visualizations. | No visualization napkin drawings.
Visualization Napkin Feedback | Visualization napkin feedback from at least 2 classmates in other groups has been documented. | Visualization napkin feedback from less than 2 classmates in other groups. Visualization napkin feedback was not documented clearly. | No visualization napkin feedback.
Visualization Napkin Feedback Consideration | Visualization napkin feedback has been incorporated into updated visualization napkin drawings. | Visualization napkin feedback has been acknowledged in feedback documentation but no updated visualization napkin drawings based on the feedback. | No visualization napkin feedback consideration.
Napkin Drawings and Feedback for Dashboard
Dashboard Napkin Drawing Quality | Dashboard napkin drawings are minimalist, little to no styling, and enough to get the point across on what is being represented. | Dashboard napkin drawings have styles that make them closer to the finished product. Dashboard napkin drawings don't clearly convey their messaging. | No dashboard napkin drawings.
Dashboard Napkin Feedback | Dashboard napkin feedback from at least 2 classmates in other groups has been documented. | Dashboard napkin feedback from less than 2 classmates in other groups. Dashboard napkin feedback was not documented clearly. | No dashboard napkin feedback.
Dashboard Napkin Feedback Consideration | Dashboard napkin feedback has been incorporated into updated dashboard napkin drawings. | Dashboard napkin feedback has been acknowledged in feedback documentation but no updated dashboard napkin drawings based on the feedback. | No dashboard napkin feedback consideration.
Kafka and Cloud ETL
Kafka Producer Stream | Kafka Producer Stream is set up and working properly. | Kafka Producer Stream was attempted but isn't set up properly or isn't working. | No Kafka Producer Stream.
Topics | Topics are set up and consumed properly. | Some topics are not set up or are not being consumed properly. | No topics are used.
Databrick | Kafka Producer Stream is captured in a Databrick properly. | Kafka Producer Stream is captured in a Databrick but not in an expected way. An attempt was made but it isn't working. | No Databrick.
Azure Data Lake | Data is migrated from Kafka into an Azure Data Lake. | Data isn't migrating properly from Kafka into the Azure Data Lake. | No Azure Data Lake.
Azure Data Factory | Azure Data Factory is moving data successfully between Azure Data Lake and Azure SQL. | Some struggles using Azure Data Factory or migrating data between Azure Data Lake and Azure SQL. | No Azure Data Factory.
Azure SQL | Azure SQL ERD and scripts work properly. | Missing ERD for Azure SQL. Scripts aren't working properly. | No Azure SQL.
Cloud Diagram | Network diagram or service diagram for pipelines is built properly. | Network diagram or service diagram for pipelines is not logically built. | No network diagram or service diagram.
Dashboard
Dash or Power BI with Python | Dashboard uses Dash or report with Power BI with Python. | Dashboard or Report created with tools other than Dash or Power BI with Python. | No dashboard present.
Messaging | Dashboard or report has clear messaging. | Dashboard or report messaging is unclear. | No dashboard or report messaging.
Visualizations | Cohesive, properly labeled, visualizations are included on the dashboard. There are enough visualizations to support the project. | Too many visualizations or not enough visualizations. Visualizations aren't cohesive. Visualizations aren't properly labeled. | No visualizations on the dashboard.
Machine Learning
Machine Learning Algorithm Used | Machine learning algorithm implemented successfully. | Machine learning algorithm attempted with some struggles. | No machine learning algorithm attempted.
Machine Learning Algorithm Tuned | Machine learning algorithm tuned for a higher accuracy. | Machine learning algorithm tuned but not optimal. | No machine learning algorithm tuning.
Machine Learning Outcomes Explained | Machine learning outcomes explained clearly. | Machine learning outcomes explained but not clearly. | No machine learning outcomes explained.
Project Technical Report
Introduction | Backstory and exploratory questions set the stage for the rest of the report clearly. | Introduction does not set clear expectations of the backstory and exploratory questions. | No introduction.
Research Presentation | Research has been presented clearly. | Research has been presented but lacks clarity. | No research presented.
Conclusion | Conclusion wraps up the research and ties back to the exploratory questions clearly. Recommendations are made. | Conclusion struggles to wrap up the research and does not tie back to the exploratory questions. Recommendations may not be made. | No conclusion.
Presentation
Introduction | Group and topic have been introduced. | Group wasn't introduced but topic was. Or group was introduced but topic wasn't. | Group and topic have not been introduced.
Initial Questions | Initial questions were proposed. | No halfway point. | Initial questions were not proposed.
Research Process | Research process was discussed clearly and showcased how they kept the initial questions in mind. | Research was discussed but the initial questions weren't kept in mind. | Research process was not described.
Machine Learning | Machine learning was discussed clearly. | Machine learning was presented but not clearly discussed. | Machine learning was not described.
Recommendations | Recommendations based on research are solid and well-defined. | Recommendations based on research are not clear. | Recommendations were not provided.